## Sheet1
No | URAIAN PEKERJAAN | NO KONTRAK | VENDOR | NILAI KONTRAK | TGL KONTRAK (dd/mm/yy) | TGL AKHIR KONTRAK (dd/mm/yy) | SISA KONTRAK (HARI) | PROGRES SAAT INI | STATUS KETERLAMBATAN | Status Jaminan Pelaksanaan | Tanggal Akhir Jaminan Pelaksanaan (dd/mm/yy) | Plan Progres (%) Terbaru | Real Progres (%) Terbaru | RENCANA AKI 2026 (Ribu Rp) | REALISASI AKI 2026 (Ribu Rp) | PROYEKSI AI LANJ 2027 (Ribu Rp) | Bidang | Unit | KONTRAK TAHUN | NO PRK | Rencana COD (dd/mm/yy)
1 | Pekerjaan Pembangunan Ulang Tower 6 Tello - Mandai | - No. Kontrak 007/DAN.01.03/PJ/F48060000/2023 - No. AMD 1284.Amd/DAN.01.03/F47010000/2024 - No. AMD II No.1363.Amd/DAN.01.03/F47010000/2024 - No. AMD III 1759.Amd/DAN.01.03/F47010000/2024 | PT Kelinci Mas Unggul | 1.751.926 | 2023-09-25 | 2024-09-18 | 0 | 4. Masa Pemeiharaan / Retensi | 2. TERLAMBAT | Ada | 2025-04-14 | 100,00% | 100,00% | 0 | 0 | 309.135 | Transmisi | UPT Makassar | 2023 | 2023.P3BL.6.002 | 2025-04-10
2 | Pengadaan dan Pemasangan Relay Proteksi Transmisi | 012/DAN.01.03/PJ/F48060000/2023 - Amandemen I : 1131.AMD/DAN.01.03/F48060000/2024 - Amandemen II : 1270.AMD/DAN. 01.03/F48060000/2024 | PT Kelinci Mas Unggul | 2. 901.429 | 2023-12-06 | 31- Agu-24 | 0 | 4. Masa Pemeiharaan / Retensi | 2. TERLAMBAT | Ada | 2026-02-24 | 0,00% | 100,00% | 1.727.804 | 1.727.804 | 21.759 | Transmisi | UPT Makassar | 2023 | 2023.P3BL.9.023 | 2025-10-10
3 | Pekerjaan Pembuatan Dinding Penahan Tanah T.257 Sidrap - Makale | 090/DAN.01.02/SPK/F48060000/2023 | PT Kelinci Mas Unggul | 260.576 | 2023-07-26 | 2024-01-21 | 0 | 4. Masa Pemeliharaan /Retensi |  |  |  | 100% | 100% | 0 | 0 | 146
4 | Pekerjaan Penggantian MTU CT UPT Makassar | 021.PJ/DAN.01.03/F47010000/2024 | PT Dipa Jaya Sejahtera | 890.883 | 2024-10-15 | 2026-03-11 | -92 | 2. Proses Pekerjaan | 1. ON SCHEDULE (TEPAT WAKTU) | Ada | 17 okt 2025 | 100,00% | 65,79% | 0 | 0 | 890.883 | Transmisi | UPT Makassar | 2024 | 2024.P3BL.9.002 | 2025-06-10
5 | Pekerjaan Penggantian MTU CVT GI Bulukumba dan GI Panakukang | 023.PJ/DAN.01.03/F47010000/2024 | PT Andekja Putra | 557.031 | 2024-10-21 | 2025-07-21 | 0 | 4. Masa pemeliharaan / Retensi | 1. ON SCHEDULE (TEPAT WAKTU) | Ada | 15 des 2025 | 0,00% | 100,00% | 557.031 | 557.031 | 0 | Transmisi | UPT Makassar | 2024 | 2024.P3BL.9.003 | 2025-09-10
6 | Pekerjaan Penggantian MTU PMT UPT Makassar | 038.SPK/DAN.01.03/F47010000/2025 | PT SEN Enjiniring Kelistrikan | 296.614 | 2025-06-20 | 2026-04-28 | -44 | 2. Proses Pekerjaan | 1. ON SCHEDULE (TEPAT WAKTU) | Tidak Ada |  | 50,00% | 50,00% | 0 | 0 | 296.614 | Transmisi | UPT Makassar | 2024 | 2024.P3BL.9.001
7 | Pekerjaan Penggantian MTU PMS Tersebar ULTG Maros | 020.PJ/DAN.01.03/F47010000/2024 | PT Andekja Putra | 1.283.915 | 2025-03-24 | 2026-03-18 | 0 | 4. Masa Pemeliharaan / Retensi | 2. TERLAMBAT | Ada | 2025-12-15 | 0,00% | 100,00% | 1.283.916 | 0 | 1.283.916 | Transmisi | UPT Makassar | 2024 | 2024.P3BL.9.004 | 2025-09-10
8 | Pekerjaan Jasa Penggantian Kapasitor Gardu Induk | 090.SPK/DAN.01.03/F47010000/2024 | PT Andekja Putra | 275.28 | 24-Des-2024 | SPMK (30 Hari) | 0 | 3. Pekerjaan Selesai | 1. ON SCHEDULE (TEPAT WAKTU) | Tidak Ada |  | 100,00% | 100,00% | 275.28 | 0 | #REF! | Transmisi | UPT Makassar | 2024 | 2024.P3BL.9.024 | 2025-08-10
9 | Pengadaan dan Penggantian Isolator Obselete Transmisi | 014.PJ/DAN.01.O3/F480600000/2024 - 1449.Amd/DAN.01.03/F47010000/2024 | KSO PT TALASALAPANG SULBAR - PT ANDEKJA PUTRA | 4.870.236 | - 29-Agu-2024 - 4-Oct-2024 | 25-Mei-2025 | 0 | 4. Masa Pemeliharaan / Retensi | 2. TERLAMBAT | Ada | 2025-09-22 | 100,00% | 100,00% | 0 | 0 | 183.15 | Transmisi | UPT Makassar | 2024 | 2024.P3BL.6.024 | 10-Okt-2025
10 | Pengadaan dan Penggantian Isolator Obselete Gardu Induk | 015.PJ/DAN.01.03/F48060000/2024 - 1450.Amd/DAN.01.03/F47010000/2024 | PT Kelinci Mas Unggul | 4.256.168 | - 29-Agu-2024 - 4-Oct-2024 | - 26-Mar-2025 | -442 | 2. Proses Pekerjaan | 2. TERLAMBAT | Ada | 2025-12-20 | 98,00% | 95,00% | 0 | 0 | 2.128.084 | Transmisi | UPT Makassar | 2024 | 2024.P3BL.6.024 | 2025-10-10
11 | Pekerjaan Pengadaan dan Pemasangan Neutral Current Transformer (GI Pangkep) | 089.SPK/DAN.01.03/F47010000/2024 | PT Andekja Putra | 283.605 | 19-Des-2024 | 2025-07-16 | 0 | 3. Pekerjaan Selesai | 2. TERLAMBAT | Tidak Ada |  | 100,00% | 100,00% | 283.605 | 0 | #REF! | Transmisi | UPT Makassar | 2024 | 2024.P3BL.9.028 | 2025-09-10
12 | Peremajaan MK GI UPT Makassar | 013.PJ/DAN.01.03/F48060000/2024 | PT Andekja Putra | 1.756.118 | 2024-08-02 | 2025-08-01 | 0 | 4. Masa Pemeliharaan / Retensi | 1. ON SCHEDULE (TEPAT WAKTU) | Ada | 2026-02-27 | 0,00% | 100,00% | 1.756.118 | 0 | 1.756.118 | Transmisi | UPT Makassar | 2024 | 2024.P3BL.9.030 | 2025-06-10
13 | Pengadaan dan Pemasangan Trafo PS GI Bakaru dan GI Balusu (Termasuk Kubikel PS) | 011.PJ/DAN.01.03/F48060000/2024 - 1448.Amd/DAN.01.03/F47010000/2024 | PT Andekja Putra | 2.157.602 | 25-Jul-2024 4-Oct-2024 | 2025-07-24 | -322 | 2. Proses Pekerjaan | 2. TERLAMBAT | Ada | 22-Des-2025 | 65,00% | 65% | 0 | 0 | 1.078.801 | Transmisi | UPT Makassar | 2024 | 2024.P3BL.9.033 | 2025-09-10
14 | Pekerjaan Penggantian MTU LA Gardu Induk Mandai 70 kV | 020.SPK/DAN.01.03/F47010000/2025 | PT Amperatech Solusindo Global | 220.912 | 26-Mei--2025 | 2026-03-23 | 0 | 4. Masa Pemeliharaan / Retensi | 1. ON SCHEDULE (TEPAT WAKTU) | Tidak ada |  | 0,00% | 100,00% | 220.912 | 0 | 220.912 | Transmisi | UPT Makassar | 2025 | 2025.P3BL.9.005
15 | Pekerjaan Penggantian MTU LA Gardu Induk Makale 150 kV | 034.SPK/DAN.01.03/F47010000/2025 | PT Talasalapang Sulbar | 102.964 | 2025-06-19 | 2026-03-22 | 0 | 4. Masa Pemeliharaan / Retensi | 1. ON SCHEDULE (TEPAT WAKTU) | Tidak ada |  | 0,00% | 100,00% | 102.964 | 0 | 102.964 | Transmisi | UPT Makassar | 2025 | 2025.P3BL.9.005
16 | Pekerjaan Penggantian MTU CVT Gardu Induk Makale 150 kV | 035.SPK/DAN.01.03/F47010000/2025 | PT SEN Enjiniring Kelistrikan | 162.069 | 2025-06-19 | 2026-03-08 | 0 | 3. Pekerjaan selesai | 1. ON SCHEDULE (TEPAT WAKTU) | Tidak ada |  | 0,00% | 100% | 162.069 | 0 | 162.069 | Transmisi | UPT Makassar | 2025 | 2025.P3BL.9.006
17 | Pekerjaan Jasa Inventarisasi ROW Reroute Tower 108 TL 150 kV Sidrap - Makale | 066.SPK/DAN.01.03/F47010000/2025 | PT Surveyor Indonesia | 181.441 | 31-Okt-2025 | SPMK 60 Hari | 0 | 2. Proses Pekerjaan | 1. ON SCHEDULE (TEPAT WAKTU) | Tidak ada |  | 0% | 0% | 0 | 0 | 181.441 | Transmisi | UPT Makassar | 2025 | 2025.P3BL.6.001
18 | Pekerjaan Pengadaan Fasilitas Monitoring Online Pemeliharaan MTU | 065.SPK/DAN.01.03/F47010000/2025 | PT Indonesia Connect Plus | 288.6 | 28-Okt-2025 | 26-Des-2025 | 0 | 4. Masa Pemeliharaan / Retensi |  | Tidak ada |  | 0% | 100% | 288.6 | 0 | 288.6 | Transmisi | UPT Makassar | 2025 | 2025.P3BL.9.004
19 | Pekerjaan Pemasangan MTU CVT Gardu Induk Panakukang 150 kV | 063.SPK/DAN.01.03/F47010000/2025 | PT Amperatech Solusindo Global | 202.02 | 13-Okt-2025 | 2026-04-03 | 0 | 4. Masa Pemeliharaan / Retensi | 1. ON SCHEDULE (TEPAT WAKTU) | Tidak ada |  | 0% | 100% | 202.02 | 0 | 202.02 | Transmisi | UPT Makassar | 2025 | 2025.P3BL.9.006
20 | Pekerjaan Perbaikan Workshop Kubikel UPT Makassar | 015.PJ/DAN.01.03/F47010000/2025 | PT Fikawan Utama | 2.534.724 | 15-Des-2025 | 12-Agu-2026 | 62 | 2. Proses Pekerjaan | 1. ON SCHEDULE (TEPAT WAKTU) | Ada |  | 23,00% | 15,00% | 0 | 0 | 2.534.724 | Transmisi | UPT Makassar | 2025 | 2025.P3BL.9.008
21 | Pekerjaan Penanganan Tower Kritis Tersebar UPT Makassar | 016.PJ/DAN.01.03/F47010000/2025 | PT Talasalapang Sulbar | 626.799 | 2026-01-05 | 2026-07-03 | 23 | 2. Proses Pekerjaan | 1. ON SCHEDULE (TEPAT WAKTU) |  |  | 95% | 100% | 626.799 | 0 | 626.799 | Transmisi | UPT Makassar | 2025 | 2025.P3BL.6.016
22 | Pekerjaan Pengadaan dan Penggantian NGR Tersebar UPT Makassar | 003.PJ/DAN.01.03/F47010000/2025 | KSO PT Earthing Resistances Indonesia - PT DIPA JAYA SEJAHTERA | 717.884 | 2025-03-25 | 2026-02-27 | 0 | 4. Masa Pemeliharaan / Retensi |  | Ada | 2026-02-27 | 0,00% | 100,00% | 281.956 | 0 | 281.956 |  |  |  |  | 2025-10-20
23 | Pekerjaan Pengadaan dan Pemasangan Peralatan Kubikel 20 kV GI Bakaru | 010.PJ/DAN.01.03/F47010000/2025 - 0223.AMD/DAN.01.03/F47010000/2026 | KSO PT TALASALAPANG SULBAR - PT ANDEKJA PUTRA | 3.895.212 | 17-Jun-25 06-Feb-26 | 2026-03-28 | -75 | 2. Proses Pekerjaan | 1. ON SCHEDULE (TEPAT WAKTU) | Ada | 2026-06-06 | 0,00% | 74,00% | 3.895.212 | 0 | 3.895.212 |  |  |  |  | 2026-02-11
24 | Pekerjaan Pengadaan dan Pemasangan Peralatan Kubikel 20 kV GI Tallo Lama | 007.PJ/DAN.01.01/F47010000/2025 | PT Kelinci Mas Unggul | 5.101.671 | 2025-06-12 | 2026-02-06 | -125 | 2. Proses Pekerjaan | 1. ON SCHEDULE (TEPAT WAKTU) | Ada | 2026-02-06 | 0,00% | 0% | 0 | 0 | 5.101.671 |  |  |  |  | 2026-02-06
25 | Pengadaan Dan Pemasangan Peralatan Kubikel 20 kV GI BARRU & GI Balusu | 005.PJ/DAN.01.03/F47010000/2025 - 029.AMD/DAN.01.03/F47010000/2026 | PT Andekja Putra | 7.981.988 | 10-Jun-2025 04-Feb-2026 | 2026-03-21 | -82 | 2. Proses Pekerjaan | 1. ON SCHEDULE (TEPAT WAKTU) | Ada | 2026-02-04 | 50% | 50% | 0 | 0 | 7.981.988 |  |  |  |  | 2026-02-04
26 | Pengadaan Dan Pemasangan Peralatan Kubikel 20 kV GI BULUKUMBA | 004.PJ/DAN.01.03/F47010000/2025 - 0210.AMD/DAN.01.03/F47010000/2026 | PT Andekja Putra | 4.500.606 | 10-Jun-2025 4-Feb-2026 | 2026-03-21 | -82 | 2. Proses Pekerjaan | 1. ON SCHEDULE (TEPAT WAKTU) | Ada | 2026-02-04 | 42% | 42% | 0 | 0 | 4.500.606 |  |  |  |  | 2026-02-04
27 | Pekerjaan Pengadaan Dan Pemasangan Peralatan Kubikel 20 kV GI Jeneponto | 009.PJ/DAN.01.03/F47010000/2025 - 0245.AMD/DAN.01.03/F47010000/2026 | KSO PT Arlisco Elektrika Perkasa -PT Jaya Cahaya Utama | 3.893.869 | 16-Jun-2025 10-Feb-2026 | 2026-03-12 | -91 | 2. Proses Pekerjaan | 1. ON SCHEDULE (TEPAT WAKTU) | Ada | 2026-09-09 | 50% | 50% | 3.893.869 | 0 | 3.893.869 |  |  |  |  | 2026-03-12
28 | Pekerjaan Pengadaan Dan Pemasangan Peralatan Kubikel 20 kV GI Makale | 008.PJ/DAN.01.03/F47010000/2025 - 0224.AMD/DAN.01.03/F47010000/2026 | PT Arisco Elektrika Perkasa | 3.893.869 | 13-Jun-2025 6-Feb-2026 | 2026-03-09 | -94 | 2. Peoses Pekerjaan | 1. ON SCHEDULE (TEPAT WAKTU) | Ada | 2026-09-05 | 50% | 50% | 3.893.869 | 0 | 3.893.869 |  |  |  |  | 2026-03-09
29 | Pekerjaan penggantian MTU CT untuk Aktivasi Buspro GI Pangkep | 012.PJ/DAN.01.03/F47010000/2025 | PT Talasalapang Sulbar | 850.342 | 5-Agu-2025 | SPMK 150 Hari | 0 | 2. Proses Pekerjaan | 1. ON SCHEDULE (TEPAT WAKTU) | Ada | 2026-06-30 | 0% | 10% | 0 | 0 | 850.342
30 | Pekerjaan penggantian MTU CT untuk Aktivasi Buspro GI Sinjai | 013.PJ/DAN.01.03/F47010000/2025 | PT Talasalapang Sulbar | 739.091 | 5-Agu-2025 | 2026-07-22 | 41 | 2. Proses Pekerjaan | 1. ON SCHEDULE (TEPAT WAKTU) | Ada | 2026-06-30 | 65% | 60% | 0 | 0 | 739.091
31 | Pekerjaan pengadaan dan penggantian isolator korosif transmisi ULTG Sidrap | 001.PJ/DAN.01.03/F47010000/2026 | KSO PT TALASALAPANG SULBAR - PT ANDEKJA PUTRA | 3.336.900 | 2026-04-30 | SPMK 300 HKL | 0 | 1. Persiapan | 1. ON SCHEDULE (TEPAT WAKTU) |  |  | 0% | 0% | 0 | 0 | 0
32 | Pengadaan dan pemasangan MRG untuk perbaikan pentanahan | 002.PJ/DAN.01.03/F47010000/2026 | PT Jaya Cahaya Utama | 1.734.441 | 13-Mei-2026 | 120 HKL terhitung sejak SPMK | 0 | 1. Persiapan | 1. ON SCHEDULE (TEPAT WAKTU) |  |  | 0% | 0% | 0 | 0 | 0
Note on L2: ====== ID#AAAB3CvB3Sc (2026-04-06 00:51:48) Selesai awal april
Note on E3: ====== ID#AAAB3CvB3Xo (2026-04-06 00:51:48) sebelum amandemen 2.901.429.000 -Konstruksi dan Penyaluran PLN UPT Makassar
Note on H3: ====== ID#AAAB3CvB3So tc={A24AABF1-3EF7-436E-8231-F58FEABBB61A} (2026-04-06 00:51:48) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ada surat teguran no. 0907/TRS.01.03/F4701000/2025, tanggal 22 Agustus 2025
Note on L3: ====== ID#AAAB3CvB3QQ tc={959CBEF7-012B-4607-B2B7-9A6FAB685443} (2026-04-06 00:51:48) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Surat perpanjangan jampel sampai 24 Feb 25 (on progress di bank overload BRI)
Note on L7: ====== ID#AAAB3CvB3SE (2026-04-06 00:51:48) Pekerjaan Selesai 18 Juni Surat perpanjangan sampai 24 Juni 2025 (Tidak ada perpanjangan jampel, menuggu penagihan)
Note on L8: ====== ID#AAAB3CvB3R0 tc={22E8054E-F828-4E65-801A-2971786EE1DF} (2026-04-06 00:51:48) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gagal padam, reschedule thn 2026, Surat Perpanjangan Jampel sampai Feb 2026 on progress di bank
Note on B10: ====== ID#AAAB3CvB3X0 tc={4AE249E9-F3B3-498C-852D-514F5CCE6B24} (2026-04-06 00:51:48) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pekerjaan selesai tanggal 17 April 2025, akan dilakukan AMD Kerja kurang
Note on E10: ====== ID#AAAB3CvB3Vo tc={756803CE-FF8B-492C-83A6-34EB5DE7D7D9} (2026-04-06 00:51:48) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: fix, kerja kurang Reply: nilai awal 4.870.086.000
Note on L10: ====== ID#AAAB3CvB3T0 tc={B191AE4B-FD80-4395-8703-06DF26887608} (2026-04-06 00:51:48) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Selesai, bulan April (ada kerja kurang)
Note on H11: ====== ID#AAAB3CvB3Sg tc={C976D3D5-05F8-489F-9DC7-24A80A1E1BFE} (2026-04-06 00:51:48) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Menunggu kurva S progress
Note on L11: ====== ID#AAAB3CvB3Rk tc={099D1096-9478-4AB7-BB80-900AD501C3A0} (2026-04-06 00:51:48) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Surat perpanjangan sampai 20 Des 2025 Reply: on progress di bank (overload BRI)
Note on H12: ====== ID#AAAB3CvB3TY tc={C3C42F06-E5B9-4479-B015-9D7C21E4BE0C} (2026-04-06 00:51:48) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Surat teguran No. 0847/DIS.01.03/F47010000/2025, 08 Ags 2025
Note on H13: ====== ID#AAAB3CvB3Xk tc={AA32FCDA-655D-445A-A849-FC870E930F8B} (2026-04-06 00:51:48) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Surat Teguran No. 0849/DIS.03.01/F4701000/2025, tgl 08 Agustus 2025
Note on H14: ====== ID#AAAB3CvB3Tc tc={C3124529-50D9-4AB5-82EE-5FA23257D376} (2026-04-06 00:51:48) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: menunggu rapat pembahasan perpanjangan waktu
Note on G21: ====== ID#AAAB3CvB3Rw tc={1690524E-C82C-4D54-B063-66E6D5492FCD} (2026-04-06 00:51:48) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 08 des 2025 (tgl kontrak) 15 Des 2025 (spmk)